## Sheet1
| Thr | Fri | Sat | Sun | Mon | Tue | Wed | Thr | Fri | Sat | Sun | Mon | Tue | Wed | Thr
Date | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06
Phase 1 | bar: 2026-07-23 to 2026-07-26
Phase 2 | bar: 2026-07-27 to 2026-07-30
Phase 3 | bar: 2026-07-31 to 2026-08-02
Phase 4 | bar: 2026-08-03 to 2026-08-05
Wrap up | bar: 2026-08-06
Phase 1 | 2026-07-23: Environment & Baseline
Goal: Prove the hardware works and the basic Python logic is sound.
Deployment | 2026-07-23: Set up the AMD ROCm environment on the Radeon cloud instance. Pull the `vllm/vllm-openai-rocm:latest` Docker image and serve a quantized base model (e.g., Llama-3-8B-Instruct) on a local endpoint (`localhost:8001/v1`).
GIS Tools | 2026-07-23: Write the deterministic Python scripts for `calculate_midpoint()` and `search_nearby_places()` using free APIs (e.g., OpenStreetMap). *Note: Do not integrate AI yet; ensure raw data is formatted cleanly.*
Agent Loop | 2026-07-23: Set up the baseline agent framework (e.g., `smolagents` or `LangChain`). Connect it to a placeholder API endpoint to verify the ReAct (Reason + Act) loop functions properly in Python.
Phase 2 | 2026-07-23: Tooling Integration & Error Handling
Goal: Connect the LLM to the tools, fulfill the Tool Invocation requirement, and fix context/hallucination errors.
Deployment | 2026-07-23: Monitor the vLLM server logs. Adjust maximum token lengths and optimize the KV-cache to prevent Out-Of-Memory (OOM) errors during heavy tool use.
GIS Tools | 2026-07-23: Write a "middleman" parser that compresses verbose POI JSON data (Name, Address, Rating) into tight, LLM-friendly strings to preserve the context window.
Agent Loop | 2026-07-23: Inject Person 2's tools into the agent prompt. Write robust Try/Catch error-handling loops so that if the LLM hallucinates a parameter, the Python script forces the LLM to correct itself instead of crashing.
Phase 3 | 2026-07-23: Memory, RAG, & UI
Goal: Implement the Local Multi-turn Memory requirement and wrap the agent in a functional user interface.
Deployment | 2026-07-23: Assist Person 3 with setting up a local vector database (e.g., ChromaDB) for the Local Knowledge Retrieval (RAG) component, ensuring the embedding model runs smoothly on the ROCm stack.
GIS Tools | 2026-07-23: Build a local SQLite database or JSON file system to save and retrieve "Friend Profiles" (e.g., dietary restrictions, preferred transit modes).
Agent Loop | 2026-07-23: Build a Streamlit or Chainlit frontend. Integrate the Friend Profiles so the agent remembers context across multi-turn interactions.
Phase 4 | 2026-07-23: Buffer, Optimization, & Submission
Goal: Implement the Local Multi-turn Memory requirement and wrap the agent in a functional user interface.
Code Freeze | 2026-07-23: No new features. The team focuses entirely on fixing bugs and stabilizing the multi-turn interaction experience.
Documentation & Media | 2026-07-23: Person 1 drafts the "Optimization description for inference speed on AMD Radeon GPU" for the Project Specification Document.
Person 2 and 3 record the 3–5 minute Demo Video, ensuring it clearly shows actual execution performance on the AMD Radeon GPU (from command line/GUI to the final result).
Final Review | 2026-07-23: Finalize the GitHub repository structure and the README file (must include environment configuration, startup guide, and dependency list).
Review the supplementary PPT/Poster.
Submit all materials via the official Pull Request process.